## Sheet1
Product Backlog Item (PBI) | Estimate | Notes
Add to cart enhancements: - Fix bug add to cart from downloads - Show # entries in cart - Ability to delete from cart - Feedback when item added to cart | 3
Website enhancements - too white, add a gradient | 1
Update text on homepage to suit target demographic | 1 | Agree stakeholders (14-25)
Checkout page (payments) - From Cart click through to entering contact and payment details - Sends email on completion to confirm order - Secure | 5
Show list of available CD albums - show Artist, Album title, Price | 3 | Qn PO - show album art?
Ability to add albums to cart. - Includes quantity - Update Cart and Checkout pages | 2 | Qn PO - maximum quantities? Estimate based on experience from Downloads (we now understand the domain and tech better)
Downloads page refinements - Add an 'All' filter to show all available downloads - Add thumbnails to tracks - Keep list of downloads at top of screen (especially when showing all tracks) - track listing not centred | 2
Landing page - advertising on landing page - new tracks and albums - special offers (BOGOF, 3for2) | 2 | Qn PO - need guidance on types of offers stakeholders would like initially.
User Registration and logon | 5
Add